## Task Sequence Matrix
Task Sequence Matrix
We cluster tasks together based on dependencies, and form design teams based on these clusters:
Task Structure Matrix (Asymmetric) X indicates that row task is dependent on column task |  | Platform Design | Language Standards | User Database | Authentication | Communication Network | User Interface | Message Database | Matchmaking Algorithm | Queuing | User Activity Monitoring | Lobby System | Scoring Metrics | Ranking | Leaderboard Display | API Linking | Data Collection | ML Research | Unit Testing | Automated Testing | User Testing
Design Rules | Platform Design |  | X
| Language Standards | X
Messaging | User Database | X |  |  | X |  |  | X | X
| Authentication | X |  | X |  |  | X | X
| Communication Network | X | X | X |  |  | X | [14 empty] | Dependency Interpretation
| User Interface | X | X | X | X | X |  | X
| Message Database |  | X | X | X |  | X |  |  |  | X
Matching | Matchmaking Algorithm |  | X | [10 empty] | X | [7 empty] | Parallel
| Queuing | X |  | X |  |  |  |  | X |  | X | X
| User Activity Monitoring | X | X |  |  |  |  | X | X | X |  | X
| Lobby System | X | [6 empty] | X | X | X |  |  | X | [7 empty] | Sequential
Scoring | Scoring Metrics |  | X | [19 empty] | X
| Ranking |  |  | X | [8 empty] | X |  | X |  | X
| Leaderboard Display | X |  |  |  |  | X | [5 empty] | X | X | [7 empty] | Coupled |  | X
Artificial Intelligence/Chatbot | API Linking | X | X | [13 empty] | X | X |  |  |  |  | X
| Data Collection |  | X |  |  | X |  |  |  |  | X |  |  |  |  | X |  | X
| ML Research | X | X | [9 empty] | X | X |  |  | X
Testing | Unit Testing | X | X |  | X | X | X | X |  | X | X | X |  | X | X | X | X |  |  | X
| Automated Testing | X | X |  |  | X |  |  | X | X | X | X | X | X |  | X |  |  | X |  | X
| User Testing | X | X | X | X |  | X |  |  |  |  | X |  |  | X |  |  |  | X | X

## Design Team Deliverables
Design Team Deliverables
We define the design rules and deliverables for each design team:
Team Index | Team | Dependent on (row) | Depended upon by (column) | Deliverables
1 | Design Rules | - | 2,3,4,5,6 | - Define platform design (communication protocol, information format and programming language) and language standards for all other teams to adhere to
2 | Messaging | 1,3 | 3,4,5,6 | - Clearly organized user database to facilitate efficient queuing (Matching) and ranking (Scoring Team) processes - Robust communication network with secure pipeline for data collection (AI/Chatbot Team) - Intuitive user interface to house leaderboard display (Scoring Team) - Exposed endpoints for testing at later stages (Testing Team)
3 | Matching | 1,2,4 | 2,5,6 | - Efficient matchmaking algorithm to simplify user database (Messaging Team) - Well-generalised user activity monitoring script to simplify message database (Messaging Team) and to facilitate data collection (AI/Chatbot Team) - Exposed endpoints for testing at later stages (Testing Team)
4 | Scoring | 1,2,5 | 3,5,6 | - Scoring metrics will determine the field of ML research (AI/Chatbot Team) to explore - Well-generalised ranking script to simplify matchmaking algorithm (Matching Team) and lobby system design (Matching Team) - Exposed endpoints for testing at later stages (Testing Team)
5 | Artificial Intelligence/Chatbot | 1,2,3,4 | 4,6 | - Data collection format may impact data types in ranking script (Ranking Team) - Exposed endpoints for testing at later stages (Testing Team)
6 | Testing | 1,2,3,4,5 | - | -

## Design Rules
Design Rules
We define the design rules for each team to adhere to:
Design Rule | Elaboration
Platform Design | To ensure modularity and compatibility between subsystems further down the line, all teams must: - Adhere to a standardized communication protocol (i.e. Just-API) - Utilise the same information format (i.e. JSON) - Implement in the same programming language (i.e. Python 3.7)
Language Standards | To ensure coherent subsystem design, all teams must: - Adhere to the same language standard (i.e. UTF-8 alphanumeric characters)