## Manual Chart
GANTT CHART
| TASK NAME | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Progress Report
| Team Formation | - | - | 100% | bar: WEEK 1 M to WEEK 3 F
| ConOps Sketch | 3 | Ryan | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 5 T to WEEK 5 Th
| To-be influence diagram | 3 | Ryan | 100% | bar: WEEK 4 M to WEEK 4 W
| Product family concept | 3 | Beverly, QZ | 100% | bar: WEEK 4 W to WEEK 4 F
| Pugh Chart | 3 | Beverly, QZ | 100% | bar: WEEK 5 T to WEEK 5 Th
| Identification of three or more abstract subsystems | 3 | Ryan | 100% | bar: WEEK 4 F to WEEK 5 T
| Presentation slides | 6 | Safa | 100% | bar: WEEK 5 Th to WEEK 6 Th
Project Requirements System Definition Documents
| Cover Page | 2 | QZ | 100% | bar: WEEK 6 Th to WEEK 6 F
| Mission Statement | 2 | Ryan | 100% | bar: WEEK 6 Th to WEEK 6 F
| User Characteristics | 5 | Safa | 100% | bar: WEEK 6 F to WEEK 7 Th
| As Is and To Be Situation Maps | 2 | Ryan | 100% | bar: WEEK 6 F to WEEK 7 M
| Operational Concept | 2 | Ryan | 100% | bar: WEEK 7 M to WEEK 7 T
| Design Alternatives | 2 | Beverly | 100% | bar: WEEK 7 M to WEEK 7 T
| Integrated Concepts | 2 | Safa | 100% | bar: WEEK 7 W to WEEK 7 Th
| Scorecard | 2 | Safa | 100% | bar: WEEK 7 F to WEEK 8 M
| Concept Selection | 2 | Safa | 100% | bar: WEEK 7 W to WEEK 7 Th
| Use Cases and Scenarios | 4 | Ryan, Beverly | 100% | bar: WEEK 8 T to WEEK 8 F
| Scenario Analysis | 4 | Ryan, Beverly | 100% | bar: WEEK 8 W to WEEK 9 M
| Chunked Design | 4 | Beverly | 100% | bar: WEEK 8 Th to WEEK 9 T
| Logical Architecture | 4 | Ryan, Beverly | 100% | bar: WEEK 7 F to WEEK 8 W
| Product Family and Release schedule | 2 | QZ | 100% | bar: WEEK 8 Th to WEEK 8 F
| Design Teams and Design Rules | 2 | Ryan | 100% | bar: WEEK 7 F to WEEK 8 M
| Modal Analysis | 4 | Ryan, Beverly | 100% | bar: WEEK 8 T to WEEK 8 F
| Non-functional requirements | 4 | QZ | 100% | bar: WEEK 7 F to WEEK 8 W
| Capella Model | 12 | Ryan, Beverly | 100% | bar: WEEK 7 T to WEEK 9 W
| Overall HTML navigation | 2 | QZ | 100% | bar: WEEK 9 Th to WEEK 9 F
Final Submission
| Game: Technical requirements | 7 | Hua Bing | 20% | bar: WEEK 9 Th to WEEK 10 F
| Game: First prototype | 5 | - | bar: WEEK 11 M to WEEK 11 F
| Game: Refinements | 3 | - | bar: WEEK 12 M to WEEK 12 W
| Video: Storyboarding | 4 | Safa | 10% | bar: WEEK 10 T to WEEK 10 F
| Video: Preparatio | 4 | - | 0% | bar: WEEK 11 M to WEEK 11 Th
| Video: Filming | 4 | - | 0% | bar: WEEK 11 F to WEEK 12 W
| Presentation slides | 2 | - | 0% | bar: WEEK 12 Th to WEEK 12 F